## Sheet1
procuring entity | package name | package description | project component | contract name | contract number | original contract sum | currency | revised contract sum | date contract agreement signed | date possession of site given | date of commencement of works | date of end of mobilization period | end date of contract | revised end date of contract | defects liability notification period | summary of scope of work | contractor | contractor address
Temeke | Package 5 | Kizinga River (TE4) | Flood Control and Storm Water Drainage | Construction of Flood Control and Storm Water Drainage System in Temeke Municipality; Package 5; Kizinga River | LGA/016/2018-2019/W/DMDP/03 | 8496720207 | TZS |  | 2019-6-3 | 2019-7-1 | 2019-7-1 | 2019-7-29 | 2020-9-29 | 2021-6-30 | 12 |  | CRJE EAST AFRICA LTD | P.O. Box 77198 Dar es Salaam
Temeke | Package 4 | Gerezani Creek (TE2; TE3; TE9) | Flood Control and Storm Water Drainage | Construction of Flood Control and Storm water Drainage System in Temeke Municipality: Gerezani Creek (TE3, TE9, TE2) | LGA/016/2018-2019/W/DMDP/02 | 18740981733 | TZS |  | 2019-6-3 | 2019-7-1 | 2019-7-1 | 2019-7-29 | 2020-9-30 | 2021-6-30 | 12 |  | China Railway Seventh Group Co. Ltd, | P. O. Box 23480, Dar es Salaam